## Sheet1
RISK ASSESSMENT
| Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
1 | Timing | Running over schedule | Low | HIGH | Developer | Fall back on MVP. | Make sure tasks are completed and marked at the end of play each day. Make sure methods are actively tested.
2 | Testing on Jenkins | Having tests run through Jenkins in the background and coverage to meet 90%+ | Medium | Medium | Developer | Ensure the coverage within terminal is at least at the minimum required percentage. | Check for syntax errors and make sure the test runs within terminal first.
3 | Bugs in code | Lines may not be fully functional and may require debugging | HIGH | Medium | Developer | Take time to debug and go through errors. | Run the code more frequently to check for error messages. Where an error appears, click to see what can be done to solve this.
4 | Computer Crash | Computer freezes requiring a restart | Low | Medium | Developer | Restart computer and other programs which were open. Inform others of the situation where possible ASAP. | Don't use uneccessary programs while coding. Make sure to constantly save work to avoid any loss in data!
5 | Secuity Leak | Information such as password and username uploaded leading to security leaks | Low | HIGH | Developer | Take Database offline and change password and potentially create a new user. | Remove sensitive data from areas which are uploaded.
6 | Input | Error messages could appear where input doesn't match the required type (ie String, Int etc) | Medium | Low | Developer | Refresh the page and input the data in the required format with the required fields filled. | Limit responses where possible using select field (drop down) and specifying required input.
7 | CSRF | Attackers on the site could input unwanted data and use unwanted commands. | Low | HIGH | Developer | Take app offline, add a secret key and reboot the application. | Use form.hidden_tag() to have a secret key that prevents this.